# Statement of Work: AI Delivery Assurance Copilot

Oct 27, 2026 · @Steve

This SOW commits to delivering a working, evaluated AI delivery-assurance copilot over 8 weeks (Oct 19 to Dec 13, 2026), built from the weekly plan in docs/plan/ROADMAP.md.

## How to read this SOW

A statement of work is the agreement on what will be delivered, when, and how we will know it is done. Each section answers one question:

| Section | The question it answers |
| --- | --- |
| Background | Why does this work exist? |
| Objectives | What outcomes count as success? |
| Scope | What is included, and just as important, what is not? |
| Deliverables | What concrete things will be handed over? |
| Schedule | When does each piece land? |
| Approach | How will the work be done, and under what rules? |
| Assumptions, constraints, risks | What must hold true, and what could go wrong? |
| Acceptance | Who signs off, and against what criteria? |

In a client engagement, Scope and Acceptance are where most disputes start, so they are the sections worth the most care.

## Background

Delivery teams lose business intent between requirements, implementation and testing, and often cannot answer: "Are we ready to release, and what evidence supports that?" Capstone 4 asks for a governed AI copilot that keeps the Requirement → Acceptance Criterion → Test → Result chain intact and explains release readiness with evidence.

This is a learning project for Steve's cohort. The goal is to understand every part well enough to explain and defend it, so understanding takes priority over speed. Sources: PROJECT_BRIEF.md, Capstone4_usecase_definition.md and the supplied dataset.

## Objectives and success criteria

The project succeeds when the copilot answers the golden scenarios with cited evidence, and Steve can explain every design decision behind it.

| Objective | Measured by |
| --- | --- |
| Answer coverage and readiness questions without AI | Deterministic gap report and readiness decision for release R26.10, every reason traceable to row IDs |
| Ground every AI output in sources | Each statement cites a document, section or row ID, or is blocked as unsupported |
| Measure quality from the first AI feature | Golden-scenario scorecard: Week 1 manual baseline as the human reference, Week 3 automated baseline, Week 8 rerun |
| Keep humans in control | No generated AC or test becomes ACTIVE without an approval record |
| Know the cost of every call | Model, tokens, latency and cost logged per call; at least two models compared |
| Generalize beyond the reference data | Set A (Jira) runs through adapters and config without editing core logic |
| Understand it all | ADRs for each major choice, a weekly journal, and a final walkthrough |

## Scope

In scope

- A normalized delivery model with provenance and origin (HUMAN, AI_SUGGESTED, AI_APPROVED) on every artifact and link

- Loading and validating the 11 reference CSVs

- Deterministic traceability queries, coverage gap reports and readiness rules

- An LLM client with TokenOps logging, and an acceptance-criteria quality classifier

- A golden-scenario evaluation harness with saved baselines

- Ingestion of the 8 PDFs, chunking with metadata, hybrid and version-aware retrieval

- Grounded generation of ACs and test cases with citations and unsupported-claim checks

- A human review gate and conflict detection across current documents

- Change impact and stale-test detection, plus an LLM explanation of the readiness decision

- Comparison of at least two models, caching and context minimization

- Onboarding Set A (Jira) through an adapter

- A minimal coverage and readiness view with drill-down to evidence

Cut order, if behind

- Sets B (Kanban) and C (Mobile Banking)

- Traceability graph view

- Agentic test execution with approval gates

- Reduce Set A to coverage only

Requirement extraction from PDFs (W4-05) is also stretch, cut as soon as Week 4 runs long.

Without W4-05, requirements come from the supplied requirements.csv, and the schema-validated AC quality classifier (W3-03) covers the brief's structured-output requirement.

Out of scope

- Production deployment, authentication or multi-user hosting

- Real Jira or Azure DevOps integration

- Editing or regenerating the source dataset, which stays read-only

- Any LLM making the readiness decision; rules decide and the LLM only explains

## Deliverables

Each deliverable maps to an issue in docs/plan/ISSUES.md and lands through its own branch and PR.

| Week | Deliverable | Issues |
| --- | --- | --- |
| 1 | Glossary and concept diagram, data profile, manual baseline for 5 golden scenarios, stack ADR | W1-01 to W1-04 |
| 2 | Delivery model ADR, one-command CSV loader with data-quality report, traceability and coverage gap report, readiness rules v0 | W2-01 to W2-04 |
| 3 | LLM wrapper with TokenOps log, 30 hand-labeled ACs, AC quality classifier, evaluation runner with baseline scorecard | W3-01 to W3-04 |
| 4 | Structured PDF extraction, chunking ADR, hybrid search with recall@k table, version-aware retrieval | W4-01 to W4-04 (W4-05 stretch) |
| 5 | Citation and unsupported-claim checks, generated ACs and test cases, review queue, conflict report | W5-01 to W5-05 |
| 6 | Change impact and stale-test lists, cited readiness summary, model comparison ADR | W6-01 to W6-03 |
| 7 | Before/after TokenOps table, adapter contract and Set A onboarding | W7-01, W7-02 (W7-03 stretch) |
| 8 | Coverage and readiness view, final evaluation vs baseline, retrospective and walkthrough | W8-01, W8-02 (W8-03, W8-04 stretch) |

Every week also produces a journal entry in docs/journal/week-NN.md.

## Schedule and milestones

capstone schedule · 8 weeks, 2 checkpoints, final defense

Each week is one milestone. The checkpoints at the end of Weeks 2 and 4 are where stretch work gets cut, early rather than late, and the Week 6 buffer for Thanksgiving comes from cutting stretch work at the Week 4 checkpoint.

## Approach and working agreements

The build order is deliberate: domain first, then the deterministic core, then AI with evaluation from day one, then generalization.

- Rules before AI. Anything a query can answer (traceability, coverage, readiness) stays deterministic. The LLM extracts, generates and explains, but never decides readiness.

- Measure from the start. The evaluation harness arrives with the first LLM feature, so every later change is compared to a baseline.

- Cite or block. Every AI output cites document, section or row IDs, or is marked unsupported.

- Human gates. Generated ACs and tests stay DRAFT until approved, with reviewer, time and diff recorded.

- Decisions are written down. Design choices go in ADRs (docs/adr/NNNN-title.md), written by Steve.

- Weekly rhythm. Start: read the week's issues and pick what to cut. During: one issue per branch and PR. End: journal entry and baseline update.

- Teaching mode. Steve writes the code by default; the assistant explains, hints and reviews.

## Assumptions, constraints and risks

Assumptions

- 8 to 10 focused hours a week are available.

- The supplied dataset and golden scenarios are the source of truth for evaluation.

- Access to at least two LLMs is available for the model comparison.

Constraints

- The dataset folder is read-only.

- API keys live in .env, never in the repo.

- No paid LLM call runs in a loop or at batch scale without a cost estimate first.

- No new dependency, framework or service without an explanation and a yes.

Risks

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Eight weeks is tight; most weeks combine two themes | High | Cut stretch work in the stated order; check progress at the end of Weeks 2 and 4 |
| Week 6 includes US Thanksgiving (Nov 26) | High | Cut stretch at the Week 4 checkpoint to free time for Week 6 |
| PDF parsing loses tables or the Doc 05 diagram | Medium | Note failures; transcribe the diagram manually if needed |
| The LLM softens or contradicts a BLOCKED decision | Medium | Rules own the decision; check the summary against it |
| LLM costs grow during evaluation runs | Medium | TokenOps logging from the first call; caching in Week 7 |
| The Week 2 model does not fit Set A | Medium | Record core changes in an ADR; treat it as a learning outcome |

## Acceptance and sign-off

Each issue is accepted when its "Done when" criteria in ISSUES.md are met and its PR is merged. The project as a whole is accepted when:

- ☐ The end-to-end scenario (§26 of the use-case definition) can be demoed

- ☐ The final evaluation is rerun and compared with the Week 3 baseline and the Week 1 manual baseline

- ☐ Every AI output in the demo cites its sources or is marked unsupported

- ☐ Every major design choice has an ADR Steve can explain and defend

- ☐ The §1P questions ("What the team should be able to explain") have prepared answers

Checkpoints: scope review at the end of Week 2 (Nov 1, 2026) and Week 4 (Nov 15, 2026); final defense by Dec 13, 2026.

Sign-off: Steve, as project owner.

Open question: does the cohort have a reviewer or instructor who should also sign off, and on what date is the defense?